## Sheet1
Project: | Start Date: | End Date: | Project Total Hours: | No of Tasks:
WAR ORT | 04 Apr 2023 | 19 Jan 2024 | 230:54 Hrs (25.6) Mandays | 29
Task Details | Task Start Date | Task End Date | Employee Name | Hours
Manager review page bug resolving | 24 Apr 2023 | 26 Apr 2023 | Smit Lalai | 02:48 Hrs
Brain storming for WAR Mobile App feature list for the first version | 24 Apr 2023 | 24 Apr 2023 | Smit Lalai | 02:29 Hrs
1) Solving Git conflicts 2)designing mail template 3)Api for attendnce graph and integration on dashboard 4)R & D ON task timer | 17 May 2023 | 17 May 2023 | Sapna Kanchar | 04:57 Hrs
1) Task Timer - code implementation 2)minor css changes on all pages 3)Dashboard- calendar integration | 18 May 2023 | 19 May 2023 | Sapna Kanchar | 09:44 Hrs
Admin Dashboard(API's for location pie chart,status,birthdays and announcements,top/under performances) Design through html css and jquery and integration of charts | 19 May 2023 | 20 May 2023 | Sapna Kanchar | 18:29 Hrs
Database connection to fetch the data from essl machine | 20 May 2023 | 20 May 2023 | Shadab Shaikh | 10:16 Hrs
1) Department filter on user dashboard page 2)Issue solving in uploaded pages of uat(changes in css,API's and testing) | 22 May 2023 | 22 May 2023 | Sapna Kanchar | 09:21 Hrs
1) Menu Item design change and database change(navbar) menuicons change 2)Forgot password email template subject 3)minor css changes on templates | 22 May 2023 | 24 May 2023 | Sapna Kanchar | 11:16 Hrs
1)Bugs solving from bug report(weekly report --listing datewise, user dashboard css) ..2)Discussion with firoz sir and team about leave module bugs and requirements | 23 May 2023 | 24 May 2023 | Sapna Kanchar | 07:29 Hrs
1)making patch for version 3.7 2)superadmin dashboard(design for whole page ,API's ,front function,integration of page ,jquery functions,Graph charts integration ) | 23 May 2023 | 26 May 2023 | Sapna Kanchar | 17:17 Hrs
Solving task time issues | 25 May 2023 | 25 May 2023 | Sapna Kanchar | 01:44 Hrs
Employee dashboard(change cards alignments as per discussion and adding birthday and announcement cards) | 29 May 2023 | 02 Jun 2023 | Sapna Kanchar | 06:05 Hrs
R&D on essl | 29 May 2023 | 30 May 2023 | Shadab Shaikh | 14:23 Hrs
Notification list integration and design (Jquery design binding,API Changes in leave module ,added dynamic modal pup ups) | 29 May 2023 | 31 May 2023 | Sapna Kanchar | 13:26 Hrs
Notfication details page (filters and list) design and integration with API and jquery | 31 May 2023 | 01 Jun 2023 | Sapna Kanchar | 12:23 Hrs
Employee dashboard--attendance table api and integration with design and filters | 01 Jun 2023 | 02 Jun 2023 | Sapna Kanchar | 08:20 Hrs
Admin Dashboard --> 1) Attendance overview graph(API and Design with integration) 2)Attendance list (API an integration) Employee dashboard(team data leavecount issue solved) | 02 Jun 2023 | 03 Jun 2023 | Sapna Kanchar | 12:02 Hrs
Admin Dashboard -Attendance list(dynamic modal pop up api and integration) | 05 Jun 2023 | 05 Jun 2023 | Sapna Kanchar | 09:31 Hrs
Excel and pdf report functionality on reports(API ,design ,jquery ) | 06 Jun 2023 | 07 Jun 2023 | Sapna Kanchar | 13:31 Hrs
Adjusting css and integration of data on admin and employee dashboards(Search functionality on team tracker , chekIn checkout disable functionality,rank data integration) | 07 Jun 2023 | 08 Jun 2023 | Sapna Kanchar | 11:55 Hrs
Responsive employee dashboard (tab view - horizontal and vertical view) also 2)solved issue with checkin and checkout | 08 Jun 2023 | 09 Jun 2023 | Sapna Kanchar | 10:42 Hrs
1)Upload patch on UAT and testing 2)solved notification images issue 3)changes in warpecent API(emp dashboard) | 12 Jun 2023 | 12 Jun 2023 | Sapna Kanchar | 10:03 Hrs
1)Integrate profile image on navbar 2)implementing Session expired redirection on all pages | 13 Jun 2023 | 13 Jun 2023 | Sapna Kanchar | 06:58 Hrs
Solving issue with weekly report time calculation | 15 Jun 2023 | 15 Jun 2023 | Sapna Kanchar | 02:52 Hrs
Responsive pages (Tab view User dashboard page ) | 17 Jun 2023 | 17 Jun 2023 | Sapna Kanchar | 00:48 Hrs
Discussion for mobile screens with the team. | 19 Jun 2023 | 19 Jun 2023 | Smit Lalai | 02:05 Hrs
1)Integrate profile image on navbar 2)implementing Session expired redirection on all pages | 26 Jul 2023 | 26 Jul 2023 | Sapna Kanchar | 00:00 Hrs
Employee dashboard(tables) | 26 Jul 2023 | 26 Jul 2023 | Sapna Kanchar | 00:00 Hrs
hiiii im test | 31 Jul 2023 | 31 Jul 2023 | Sapna Kanchar | 00:00 Hrs